## Builders
Name | Handle | Source channel | Source link | Template | DM channel | Date sent | Reply received? | Date of reply / call | Conversation held? | Pain named | Would pay 1-3%? | Use case | Written interest? | Notes | Next step
Alice Doe | @alice_x402 | GitHub: coinbase/x402 | https://github.com/coinbase/x402/pull/123 | B | X DM | [8 empty] | Found via PR #123 — works on facilitator infra | Send template B today
Bob Smith | @bob_builds | X search | https://x.com/bob_builds/status/1700000000000000000 | A | X DM | 2026-04-29 | No |  | No |  |  |  | No | Sent template A; tweet was a launch demo of an x402-paid search agent | Wait 4 days, then one polite follow-up
Carol Lee | @carol_dev | CDP Discord #x402 | https://discord.com/channels/.../... | D | Discord DM | 2026-04-28 | Yes | 2026-04-29 | Yes | Spend limits | Yes | Wallet-aware shopping agent on Base; processes ~200 paid calls/day | Yes | Said: 'spend limits is the part I'm scared of — would happily pay 1-2% to outsource the kill-switch + per-call price cap' | Send Phase 3 design sketch when ready

## Phase 2 status
Phase 2 — outreach status
Auto-updates from the Builders tab. Phase 2 is done when all three gates show OK.
Counts
Builders contacted | 3
Replies received | 1
Conversations held | 1
Written "yes, I'd pay" | 1
Reply rate | 33.33%
Conversation rate | 33.33%
Phase 2 gates
≥6 builders contacted | Need 3
≥3 conversations held | Need 2
≥1 written "yes I'd pay" | OK
Status | Not yet
Pain points named |  | Most-named pain shapes Phase 3 build order.
Discovery | 0
Signing | 0
Retries | 0
Spend limits | 1
Accounting | 0
Other | 0
Most-named pain | Spend limits
How to use this sheet
1. Fill rows on the Builders tab as you contact people. Dropdowns for Yes/No, pain, etc.
2. The counts and gates above auto-update.
3. Phase 2 is done when all three gates show OK and Status reads 'PHASE 2 DONE'.
4. The "Most-named pain" cell decides which Phase 3 sub-feature to ship after the router primitive (signing/retries/spend limits/accounting).
5. Three example rows are pre-filled on the Builders tab so you can see the format. Delete them once you have real data.